## Test Plan
PARABANK ROBOT FRAMEWORK CAPSTONE — MANUAL TEST PLAN
PURPOSE | Validate end-to-end account lifecycle and fund transfer flows across UI and API layers, ensuring data consistency, correctness, and proper error handling for the ParaBank demo banking application.
SCOPE | • Account creation via UI (FR-01) • Account retrieval & validation via API (FR-02, FR-03, FR-04) • Fund transfer via UI (FR-05) • Balance & transaction validation via API (FR-06, FR-07) • UI success/error message validation (FR-08) • Negative & boundary scenarios (FR-09) • Hybrid (UI + API) end-to-end flows
APPLICATION | ParaBank Demo Banking App UI: https://parabank.parasoft.com API Swagger: https://parabank.parasoft.com/parabank/api-docs/index.html
TEST APPROACH | • Functional UI Testing (SeleniumLibrary + Robot Framework + Chrome/Firefox) • API Testing (RequestsLibrary + Basic Auth) • Hybrid E2E Testing (UI action → API verification) • Negative / Boundary Testing • Performance-Lite checks (response time + concurrency)
ENVIRONMENTS | • Browser: Chrome, Firefox • OS: Ubuntu (CI/CD), Windows (local) • Python 3.11+ • Framework: Robot Framework + SeleniumLibrary / RequestsLibrary
ENTRY CRITERIA | • ParaBank app is reachable at https://parabank.parasoft.com • Test credentials (username/password) are active • Robot Framework environment is installed and configured • API Swagger documentation is accessible
EXIT CRITERIA | • All smoke tests pass • ≥ 90% test case pass rate achieved • All Critical/High defects resolved or formally deferred • Test Summary Report prepared and signed off
TEST TYPES | 1. UI Functional Tests — Login, Registration, Account Creation, Fund Transfer, Loan, Negative 2. API Tests — GET Accounts, GET Account by ID, Create Account, Transfer, Schema & Type Validation 3. Hybrid E2E — UI create → API verify, UI transfer → API balance check 4. Performance Lite — API response time < 2s, 20 concurrent requests
OUT OF SCOPE | • Real banking or financial transactions • Security or penetration testing • Mobile / responsive UI testing • Full load or stress testing beyond lightweight performance checks
RISKS & MITIGATIONS | • Demo site may reset data periodically → Use dynamic test data generation • Multiple testers sharing accounts → Use isolated account creation flows • API rate limiting on demo env → Add request throttling in performance suite • Network latency on demo env → Add retry logic for flaky assertions
FRAMEWORK | Robot Framework + Python (POM + API Fixtures + Parallel Execution via Pabot)
AUTOMATION STACK | • SeleniumLibrary for UI • RequestsLibrary for API • Pabot for parallel execution • Allure for reporting • GitHub Actions for CI/CD
PREPARED BY | Candidate Name
VERSION | 1.0 — June 2026

## Test Scenarios
TEST SCENARIOS — ParaBank Robot Framework Capstone
Scenario ID | Scenario Name | Description | FR Coverage | Test Type
TS-01 | User Registration | Verify user registration functionality with valid and invalid inputs. | FR-01 | UI Functional
TS-02 | Account Creation | Verify users can create different account types (Checking, Savings, Loan) through UI and API. | FR-01, FR-08 | UI/API Functional
TS-03 | User Authentication | Verify login and logout functionality with valid and invalid credentials. | FR-09 | UI Functional
TS-04 | Account Information Retrieval | Verify account details, account lists, and transaction history can be retrieved correctly. | FR-02, FR-03, FR-04 | API Functional
TS-05 | Fund Transfer | Verify successful fund transfer between accounts through UI and API. | FR-05, FR-06, FR-07, FR-08 | UI/API Functional
TS-06 | Input Validation & Error Handling | Verify application handles invalid transfers, invalid credentials, duplicate users, and other negative scenarios correctly. | FR-05, FR-09 | Negative Testing
TS-07 | End-to-End Business Flow Validation | Verify UI actions are reflected correctly in backend APIs. | FR-01 to FR-07 | E2E Testing
TS-08 | API Schema & Data Validation | Verify API responses contain correct fields, data types, and business values. | FR-02, FR-03, FR-04 | API Validation
TS-09 | Performance Validation | Verify API response times and concurrent request handling meet requirements. | FR-02 | Performance

## Test Cases
TEST CASES — ParaBank Robot Framework Capstone
TC ID | Scenario ID | Test Case Name | Test Type | Pre-conditions | Test Steps | Expected Result | Actual Result | FR Coverage | Status
TC-UI-01 | TS-01 | Register New User with Valid Data | UI | App is accessible | 1. Navigate to Register page 2. Fill all mandatory fields with valid data 3. Click Register | Registration successful; user lands on overview page or can login | Registration successful; user lands on overview page or can login | FR-01 | Pass
TC-UI-02 | TS-01 | Register User with Password and Confirm Password Mismatch | UI | App is accessible | 1. Navigate to Register page 2. Fill all mandatory fields with valid data 3. Password and confirm password field should not be same. 4.Click Register | Registration unsuccessful; user get a prompt "Passwords did not match" | Registration unsuccessful; user get a prompt "Passwords did not match" | FR-01 | Pass
TC-UI-03 | TS-01 | Register User with Empty/Blank Fields | UI | App is accessible | 1. Navigate to Register page 2. Leave all the fields empty 3. Click Register | Registration unsuccessful; user gets a prompt "fields are required." | Registration unsuccessful; user gets a prompt "fields are required." | FR-01 | Pass
TC-UI-04 | TS-01 | Register User That Is Already Exsisting | UI | App is accessible | 1. Navigate to Register page 2. Fill all mandatory fields with valid data of an existing user. 3. Click Register | Registration unsuccessful; user gets a prompt "This username already exists." | Registration unsuccessful; user gets a prompt "This username already exists." | FR-01 | Pass
TC-LGN-01 | TS-04 | Authenticate with Valid Credentials | UI | App is accessible | 1. Open /parabank/index.htm 2. Enter valid username 3. Enter valid password 4. Click Log In | User lands on Account Overview page; URL contains 'overview' | User lands on Account Overview page; URL contains 'overview' | FR-09 | Pass
TC-NEG-LGN-02 | TS-05 | Authenticate with Invalid Credentials | UI | App is accessible | 1. Open /parabank/index.htm 2. Enter username: abc 3. Enter password: lkj 4. Click Log In | Error message displayed; user stays on login page; URL does NOT contain 'overview' | Error message displayed; user stays on login page; URL does NOT contain 'overview' | FR-09 | Pass
TC-NEG-LGN-03 | TS-06 | Authenticate with Empty Credentials | UI | App is accessible | 1. Open /parabank/index.htm 2. Leave both fields blank 3. Click Log In | User NOT redirected to overview; login blocked | User NOT redirected to overview; login blocked | FR-09 | Pass
TC-LGN-04 | TS-07 | Logout from Application | UI | User is logged in | 1. Login to application 2. Click Logout link | User is logged out; redirected to login/home page | User is logged out; redirected to login/home page | FR-09 | Pass
TC-OA-UI-01 | TS-02 | Open New CHECKING Account via UI | UI | User is logged in | 1. Navigate to 'Open New Account' 2. Select Account Type: CHECKING (value=0) 3. Pick source account 4. Click 'Open New Account' | Congratulations header visible; new account ID link rendered | Congratulations header visible; new account ID link rendered | FR-01, FR-08 | Pass
TC-OA-UI-02 | TS-03 | Open New SAVINGS Account via UI | UI | User is logged in | 1. Navigate to 'Open New Account' 2. Select Account Type: SAVINGS (value=1) 3. Pick source account 4. Click 'Open New Account' | Congratulations header visible; new account ID link rendered | Congratulations header visible; new account ID link rendered | FR-01, FR-08 | Pass
TC-TF-01 | TS-08 | Transfer Funds Between Two Accounts via UI | UI | User logged in; at least 2 accounts exist | 1. Create destination account via UI 2. Go to Transfer Funds page 3. Enter transfer amount 4. Select source/destination accounts 5. Click Transfer | 'Transfer Complete!' heading visible; amount reflects entered value | 'Transfer Complete!' heading visible; amount reflects entered value | FR-05, FR-08 | Pass
TC-NEG-TF-02 | TS-20 | Transfer Amount Greater Than The Balance – Should Be Rejected | UI | User logged in; at least 1 account exists | 1. Go to Transfer Funds 2. Select the same account in both From and To 3. Enter amount: 100 4. Click Transfer | Error or warning displayed; transfer should NOT complete. | Transfer Complete!' | FR-05, FR-09 | Defect
TC-NEG-TF-03 | TS-20 | Transfer to Same Account – Should Be Rejected | UI | User logged in; at least 1 account exists | 1. Go to Transfer Funds 2. Select the same account in both From and To 3. Enter amount: 100 4. Click Transfer | Error or warning displayed; transfer should NOT complete when source = destination | Transfer Complete!' | FR-05, FR-09 | Defect
TC-NEG-TF-04 | TS-21 | Transfer with Negative Amount – Should Be Rejected | UI | User logged in; 2 accounts exist | 1. Go to Transfer Funds 2. Enter amount: -100 3. Select source/destination 4. Click Transfer | Validation error shown; transfer rejected | 'Transfer Complete!' | FR-05, FR-09 | Defect
TC-NEG-TF-05 | TS-22 | Transfer with Zero Amount – Should Be Rejected | UI | User logged in; 2 accounts exist | 1. Go to Transfer Funds 2. Enter amount: 0 3. Select source/destination 4. Click Transfer | Validation error shown; zero-amount transfer rejected | 'Transfer Complete!' | FR-05, FR-09 | Defect
TC-API-01 | TS-10 | Test Login via API | API | Valid credentials available | 1. Send GET /login/{username}/{password} 2. Inspect status code | Status 200 OK; response body confirms login | Status 200 OK; response body confirms login | FR-09 | Pass
TC-API-02 | TS-11 | GET Customer Accounts Validate Status Code | API | Valid Basic Auth; customer exists | 1. Send GET /customers/{customerId}/accounts 2. Include Authorization header 3. Inspect status and body | Status 200; response is JSON array; each item has id, customerId, type, balance | Status 200; response is JSON array; each item has id, customerId, type, balance | FR-02 | Pass
TC-API-03 | TS-12 | GET Account Details by ID | API | At least one account exists | 1. GET customer accounts — capture first ID 2. Send GET /accounts/{id} 3. Validate all fields | id matches; type is string; balance is number; customerId is correct | id matches; type is string; balance is number; customerId is correct | FR-03, FR-04 | Pass
TC-API-04 | TS-13 | GET Transactions for Account ID | API | Account with given ID exists | 1. Capture account ID from customer accounts 2. Send GET /accounts/{id}/transactions 3. Validate response | Status 200; response is array; if non-empty, each transaction has id, amount, type | Status 200; response is array; if non-empty, each transaction has id, amount, type | FR-02 | Pass
TC-API-05 | TS-14 | Create CHECKING Account via API | API | Valid Auth; customer exists | 1. POST to create account endpoint with type=CHECKING 2. Inspect status and body | Status 200; new account object returned with id | Status 200; new account object returned with id | FR-01 | Pass
TC-API-06 | TS-14 | Create SAVINGS Account via API Returns 200 | API | Valid Auth; customer exists | 1. POST to create account endpoint with type=SAVINGS 2. Inspect status and body | Status 200; new account object returned with id | Status 200; new account object returned with id | FR-01 | Pass
TC-API-07 | TS-14 | Create LOAN Account via API | API | Valid Auth; customer exists | 1. POST to create account endpoint with type=LOAN 2. Inspect status and body | Status 200; new account object returned with id | Status 200; new account object returned with id | FR-01 | Pass
TC-API-08 | TS-15 | Transfer Funds via API | API | Two accounts exist with sufficient balance | 1. Create two accounts via API 2. POST /transfer with fromAccountId, toAccountId, amount=100 3. GET both accounts and check balances | Transfer succeeds; source balance decreases by 100; destination balance increases by 100 | Transfer succeeds; source balance decreases by 100; destination balance increases by 100 | FR-05, FR-06, FR-07 | Pass
TC-API-09 | TS-16 | Validate Account Fields and Data Types | API | Accounts exist for customer | 1. GET /customers/{id}/accounts 2. Iterate each account 3. Validate id>0, customerId>0, type in [CHECKING,SAVINGS,LOAN], balance is numeric | All accounts pass field and data type validation | All accounts pass field and data type validation | FR-03, FR-04 | Pass
TC-E2E-01 | TS-17 | Create CHECKING Account via UI → Validate Exists via API | Hybrid | User logged in; API accessible | 1. Create new CHECKING account via UI 2. Capture new account number from UI 3. Call GET /accounts/{id} via API 4. Compare account ID from UI vs API | Account ID from UI matches id in API response | Account ID from UI matches id in API response | FR-01, FR-02, FR-03 | Pass
TC-E2E-02 | TS-18 | Create Account via UI → Validate Account Type via API | Hybrid | User logged in; API accessible | 1. Create CHECKING account via UI 2. Capture account number 3. Call GET /accounts/{id} via API 4. Assert type == CHECKING | API returns type = 'CHECKING' matching what was selected in UI | API returns type = 'CHECKING' matching what was selected in UI | FR-03, FR-04 | Pass
TC-E2E-03 | TS-19 | UI Fund Transfer → Validate Balance Delta via API | Hybrid | User logged in; 2 accounts exist; API accessible | 1. GET balances of both accounts via API (before) 2. Transfer $100 via UI 3. GET balances via API (after) 4. Assert source balance decreased by 100 5. Assert destination balance increased by 100 | Source balance = before - 100; destination balance = before + 100 | Source balance = before - 100; destination balance = before + 100 | FR-05, FR-06, FR-07 | Pass
TC-PERF-01 | TS-25 | API Response Time Under 2 Seconds | API/Performance | API accessible | 1. Record start time 2. GET /customers/{id}/accounts 3. Record end time 4. Assert elapsed < 2000ms | Elapsed time < 2000ms; status 200 | Elapsed time < 2000ms; status 200 | FR-02 | Pass
TC-DD-01 | TS-26 | 5 Concurrent API Requests | API/Performance | API accessible; valid credentials | 1. Build 5 GET requests to get account details. 2. Execute all asynchronously 3. Assert all responses | All 5 responses return HTTP 400 as all are invaild creds | All 5 responses return HTTP | FR-02 | Pass

## RTM
REQUIREMENT TRACEABILITY MATRIX (RTM) — ParaBank Robot Framework Capstone
FR ID | Requirement | Scenario(s) | Test Case(s)
FR-01 | User registration and account creation | TS-01, TS-02, TS-07 | TC-UI-01, TC-UI-02, TC-UI-03, TC-UI-04, TC-OA-UI-01, TC-OA-UI-02, TC-API-05, TC-API-06, TC-API-07, TC-E2E-01
FR-02 | Retrieve account and transaction information | TS-04, TS-07, TS-08, TS-09 | TC-API-02, TC-API-04, TC-API-09, TC-E2E-01, TC-PERF-01, TC-DD-01
FR-03 | Validate account existence and account details | TS-04, TS-07, TS-08 | TC-API-03, TC-API-09, TC-E2E-01, TC-E2E-02
FR-04 | Validate account type and account information | TS-04, TS-07, TS-08 | TC-API-03, TC-API-09, TC-E2E-02
FR-05 | Fund transfer functionality | TS-05, TS-06, TS-07 | TC-TF-01, TC-API-08, TC-E2E-03, TC-NEG-TF-02, TC-NEG-TF-03, TC-NEG-TF-04, TC-NEG-TF-05
FR-06 | Validate balance updates after transfer | TS-05, TS-07 | TC-API-08, TC-E2E-03
FR-07 | Validate transfer balance calculations | TS-05, TS-07 | TC-API-08, TC-E2E-03
FR-08 | Validate success and confirmation messages | TS-02, TS-05 | TC-OA-UI-01, TC-OA-UI-02, TC-TF-01
FR-09 | Authentication and negative validations | TS-03, TS-06 | TC-LGN-01, TC-NEG-LGN-02, TC-NEG-LGN-03, TC-LGN-04, TC-API-01, TC-NEG-TF-02, TC-NEG-TF-03, TC-NEG-TF-04, TC-NEG-TF-05

## Code Review & Gap Analysis
CODE REVIEW & GAP ANALYSIS — Robot Framework Test Suite
Area / File | Issue / Observation | Severity | Recommendation | Status
Project Structure | Structure follows the prescribed layout: resources/keywords/, resources/pages/, tests/ui/, tests/api/, tests/e2e/, variables/, config/ ✔ Aligns with Section 2.1 requirements. | OK | No changes needed — structure is correct. | ✔ OK
test_create_account.robot | All three test cases share the same ID 'TC-API-12'. Robot Framework requires unique test names within a suite. | High | Rename to TC-API-12 (CHECKING), TC-API-13 (SAVINGS), TC-API-14 (LOAN). | ❌ Fix Required
test_fund_transfer.robot | Negative test cases (same account, negative amount, zero amount) are commented out. FR-09 requires negative scenario coverage. These are critical bugs logged as defects. | High | Uncomment and implement the negative transfer scenarios. | ❌ Fix Required
test_open_new_account.robot | TC-OA-UI-02 is labelled 'Open New SAVINGS Account' but passes type=CHECKING. The test name contradicts the implementation. | High | Fix the label or the keyword argument — it should pass type=SAVINGS for a SAVINGS test. | ❌ Fix Required
test_get_account_details.robot | ${account_Id} is set but ${accountId} is used in the GET call (case mismatch). Robot Framework variable names are case-sensitive. | High | Standardise to ${account_id} throughout the file. | ❌ Fix Required
Suite Setup – Missing on Some Files | test_open_new_account.robot is missing 'Suite Setup Load Environment'. Global variables (${USERNAME}, ${PASSWORD}, ${BASE_URL}) won't be loaded. | High | Add 'Suite Setup Load Environment' to test_open_new_account.robot. | ❌ Fix Required
Negative API Tests | No test file covers: • API with wrong Basic Auth credentials • API with non-existent customer ID These map to FR-09 and TS-23/TS-24. | High | Create test_api_negative.robot with TC-NEG-API-01 and TC-NEG-API-02. | ❌ Missing
Performance Tests | Section 3.5 requires: • Capture API response times • Fail if API > 2 seconds • 20 async GET requests No performance test file exists in the project. | High | Create tests/performance-lite/test_performance.robot with TC-PERF-01 and TC-PERF-02. | ❌ Missing
Allure Report Integration | Section 2.4.2.7 requires Allure report integration with screenshots. No Allure listener config or @allure decorators observed in the code. | Medium | Add robotframework-allure-listener to requirements.txt and configure in robot run command. | ❌ Missing
CI/CD Pipeline | Section 3.2 requires a GitHub Actions YAML (or Jenkins). No .github/workflows/ directory is present in the project. | High | Create .github/workflows/robot_tests.yml with steps for install, run, and publish HTML/Allure report. | ❌ Missing
Pabot Parallel Execution | Section 3.1.1 requires Pabot for parallel execution. pabot is not listed in requirements.txt. | Medium | Add robotframework-pabot to requirements.txt and create a pabot config file. | ❌ Missing
MCP / RobotMCP Integration | Section 3.4 requires RobotMCP integration for script generation and execution. Not implemented. | Medium | Implement basic RobotMCP integration as per Section 3.4 requirements. | ❌ Missing
AI-Assisted Test Data | Section 3.3 requires AI-generated test data utility (e.g. GitHub Copilot generated random data). Not observed in the codebase. | Medium | Create utils/test_data_generator.py and use AI-generated data in automation scripts. | ❌ Missing
AI Failure Analysis Report | Section 3.3 requires an AI-generated HTML failure analysis report with failure count, reason, historical analysis. Not implemented. | Medium | Create utils/failure_analysis.py that generates HTML report from Robot output.xml. | ❌ Missing
Tagging | Section 3.1.2 requires test tagging: @smoke, @regression, @api, @e2e. No [Tags] metadata observed in any test file. | Medium | Add [Tags] to each test case. Example: [Tags] smoke regression ui | ❌ Missing
Data-Driven Tests | Section 3.1.2 requires data-driven tests using CSV/JSON. Not implemented. | Low | Implement at least one data-driven test using Robot Framework's data-driven style or external CSV/JSON. | ❌ Missing
Smart Waiting | Section 2.2 recommends 'Smart Waiting Instead of Sleep'. No explicit Sleep calls detected — good practice followed. | OK | Continue using wait_until/explicit waits from SeleniumLibrary. | ✔ OK
Fresh Browser Context | Test Setup / Test Teardown with Open Application / Close Application in every suite. ✔ Aligns with Section 2.2 best practice. | OK | Good practice — keep this pattern. | ✔ OK
API Logging | Section 2.3 requires all API requests and responses to be logged. Log To Console is used in API tests but not structured logging. | Low | Use Robot Framework's built-in LOG keyword and Python logging module for structured API logs. | ⚠ Improve
Cross Validation File Naming | test_cross_validation.robot, test_cross_validation1.robot, test_cross_validation2.robot. All three files contain a test named 'E2E-01' — names should be unique and descriptive. | Medium | Rename files and test cases: test_e2e_account_exists.robot, test_e2e_account_type.robot, test_e2e_fund_transfer.robot | ❌ Fix Required

## Test Execution Report
TEST EXECUTION SUMMARY — ParaBank Robot Framework Capstone
Project | ParaBank Robot Framework Capstone
Executed By | Candidate Name
Execution Date | June 2026
Environment | https://parabank.parasoft.com ¦ Python 3.11 ¦ Robot Framework
Total Test Cases | 25
Pass | 22
Fail | 0
Blocked | 0
Not Implemented | 0
Pass Rate | #VALUE!
TC ID | Test Case Name | Type | Tags | Browser/Tool | Status | Execution Time | Defect ID
TC-UI-01 | Register New User with Valid Data | UI | smoke, regression | Chrome | Pass | ~5s | —
TC-LGN-01 | Authenticate with Valid Credentials | UI | smoke, regression | Chrome | Pass | ~3s | —
TC-LGN-02 | Authenticate with Invalid Credentials | UI | smoke, regression, negative | Chrome | Pass | ~3s | —
TC-LGN-03 | Authenticate with Empty Credentials | UI | negative | Chrome | Pass | ~2s | —
TC-LGN-04 | Logout from Application | UI | regression | Chrome | Pass | ~2s | —
TC-OA-UI-01 | Open New CHECKING Account via UI | UI | smoke, regression | Chrome | Pass | ~8s | —
TC-OA-UI-02 | Open New SAVINGS Account via UI | UI | regression | Chrome | Pass | ~8s | —
TC-TF-UI-01 | Transfer Funds Between Two Accounts via UI | UI | smoke, regression | Chrome | Pass | ~10s | —
TC-NEG-UI-03 | Transfer Amount Greater Than The Balance – Should Be Rejected | UI | defect | Chrome | Defect |  | DEF-001
TC-NEG-UI-01 | Transfer to Same Account – Should Be Rejected | UI | defect | Chrome | Defect | — | DEF-002
TC-NEG-UI-02 | Transfer with Negative Amount – Should Be Rejected | UI | defect | Chrome | Defect | — | DEF-003
TC-NEG-UI-03 | Transfer with Zero Amount – Should Be Rejected | UI | defect | Chrome | Defect | — | DEF-003
TC-API-01 | Test Login via API | API | api, smoke | RequestsLibrary | Pass | ~1s | —
TC-API-02 | GET Customer Accounts Returns 200 and JSON Array | API | api, regression | RequestsLibrary | Pass | ~1s | —
TC-API-03 | GET Account Details by ID Returns Correct Payload | API | api, regression | RequestsLibrary | Pass | ~1s | —
TC-API-04 | GET Transactions for Account Returns Valid Array | API | api | RequestsLibrary | Pass | ~1s | —
TC-API-05 | Create CHECKING Account via API Returns 200 | API | api, regression | RequestsLibrary | Pass | ~1s | —
TC-API-06 | Create SAVINGS Account via API Returns 200 | API | api, regression | RequestsLibrary | Pass | ~1s | —
TC-API-07 | Create LOAN Account via API Returns 200 | API | api | RequestsLibrary | Pass | ~1s | —
TC-API-08 | Transfer Funds via API Updates Balances | API | api, smoke, regression | RequestsLibrary | Pass | ~2s | —
TC-API-09 | Validate Account Fields and Data Types | API | api, regression | RequestsLibrary | Pass | ~1s | —
TC-E2E-01 | Create CHECKING Account via UI → Validate via API | Hybrid | e2e, smoke | Chrome + RequestsLibrary | Pass | ~12s | —
TC-E2E-02 | Create Account via UI → Validate Account Type via API | Hybrid | e2e, regression | Chrome + RequestsLibrary | Pass | ~12s | —
TC-E2E-03 | UI Fund Transfer → Validate Balance Delta via API | Hybrid | e2e, smoke | Chrome + RequestsLibrary | Pass | ~18s | —
TC-PERF-01 | API Response Time Under 2 Seconds | Performance | performance | RequestsLibrary | Pass | — | —
TC-PERF-02 | 5 Concurrent API Requests All Return 200 | Performance | performance | RequestsLibrary | Pass | — | —

## Defect Report
DEFECT REPORT — ParaBank Robot Framework Capstone
Defect ID | TC ID | Title | Steps to Reproduce | Expected | Actual | Severity | Status
DEF-001 | TC-NEG-TF-04 | Negative Amount Transfer | 1. Login 2. Go to Transfer Funds 3. Enter amount: -100 4. Select source/destination 5. Click Transfer | Validation error: 'Amount must be greater than zero' | Transfer completes with negative amount — no error shown and reverse transaction occurs | High | Open
DEF-002 | TC-NEG-TF-05 | Zero Amount Transfer | 1. Login 2. Go to Transfer Funds 3. Enter amount: 0 4. Select accounts 5. Click Transfer | Validation error: 'Amount must be greater than zero' | '$0.00 transferred' — zero transfer succeeds | High | Open
DEF-003 | TC-NEG-TF-03 | Self-Transfer Allowed — Same Account as Source and Destination | 1. Login 2. Go to Transfer Funds 3. Select same account in both From and To 4. Enter amount: 100 5. Click Transfer | Error: 'Source and destination accounts cannot be the same' | Transfer completes — self-transfer recorded as valid | High | Open
DEF-004 | TC-NEG-TF-02 | Amount Greater Than the Account Balance | 1. Login 2. Go to Transfer Funds 3. Enter amount: 0 4. Select accounts 5. Click Transfer | Validation error: 'Amount can't be greater than the account balance' | Transfer completes — and the balance of the source account is negative | High | Open

## Test Summary Report
FINAL TEST SUMMARY REPORT — ParaBank Robot Framework Capstone
PROJECT | ParaBank Robot Framework Capstone
AUTHOR | Candidate Name
DATE | June 2026
OBJECTIVE | Validate end-to-end account lifecycle and fund transfer flows using Robot Framework across UI, API, and Hybrid layers — ensuring data integrity, response correctness, and error handling.
── EXECUTION SUMMARY ──
Total Test Cases Designed | 29
Total Test Cases Automated | 20
Total Test Cases Executed | 20
Passed | 20
Failed | 0
Blocked | 0
Not Implemented | 9 (Negative + Performance TCs)
Pass Rate (Executed) | 100% (20/20)
── TEST TYPE BREAKDOWN ──
UI Tests | 9 automated — 9 Passed
API Tests | 9 automated — 9 Passed
Hybrid E2E Tests | 3 automated — 3 Passed
Performance Tests | 0 implemented — 2 required by Section 3.5
Negative Tests | 3 UI negatives commented out; 2 API negatives not created
── REQUIREMENTS COVERAGE ──
FR-01 – Create account via UI | ✔ Covered
FR-02 – GET accounts via API | ⚠ Partially — performance checks missing
FR-03 – Validate account exists in API | ✔ Covered
FR-04 – Validate account type and details | ✔ Covered
FR-05 – Transfer funds via UI | ⚠ Partially — negative transfer TCs commented out
FR-06 – Validate updated balances via API | ✔ Covered
FR-07 – Validate transfer before/after | ✔ Covered
FR-08 – Validate UI messages | ✔ Covered
FR-09 – Validate negative scenarios | ⚠ Partially — several negative TCs missing/commented
Overall FR Coverage | 7/9 fully covered ¦ 2/9 partially covered
── DEFECTS SUMMARY ──
Total Defects Found | 8
Critical | 0
High | 7 (DEF-001 to DEF-007)
Medium | 1 (DEF-005)
Low | 0
Application Bugs | DEF-001, DEF-002, DEF-003 (transfer validation)
Automation/Code Bugs | DEF-004 (duplicate IDs), DEF-005 (wrong type), DEF-006 (variable), DEF-007 (suite setup)
── AUTOMATION FRAMEWORK ──
Framework | Robot Framework + Python
Pattern | POM + API Fixtures + (Pabot for parallel — not yet configured)
Browsers | Chrome
Reporting | Robot Framework Built-in (log.html, report.html)
CI/CD | Not implemented — GitHub Actions YAML required
── MISSING SECTIONS (Action Required) ──
Parallel Execution (Pabot) | Not configured — Section 3.1.1 requirement
CI/CD Pipeline | No .github/workflows/ YAML — Section 3.2 requirement
AI-Driven Enhancements | Test data generator and failure analysis report not implemented — Section 3.3
MCP Integration | RobotMCP not implemented — Section 3.4 requirement
Performance Tests | Performance suite not created — Section 3.5 requirement
Allure Reports | Not configured — Section 2.4.2.7 requirement
── SIGN-OFF ──
Recommendation | Core automation (UI + API + Hybrid) is implemented and passes. Multiple required sections are incomplete: CI/CD, performance, Allure, AI enhancements, negative TCs, and MCP. Code quality issues (duplicate IDs, variable mismatch, missing suite setup) must be fixed before final submission.